## Recommendations
Recommendation ID | Area | Business Finding | Recommendation | Priority
REC-001 | Demand | Whitefield and Electronic City have high booking demand | Review vehicle capacity for high-demand routes | High
REC-002 | Vehicle Utilization | Several vehicles have low utilization | Consider smaller vehicles on low-demand routes | High
REC-003 | Route Planning | Some routes have low booking demand | Review route frequency and vehicle allocation | Medium
REC-004 | Delay | Traffic is the main reason for delays | Review pickup schedules and allow additional travel time during peak hours | High
REC-005 | Cancellation | Bellandur route had a vehicle breakdown cancellation | Maintain backup vehicle availability for critical routes | High
REC-006 | Cost | Transportation cost varies across vendors and routes | Compare vendor cost and service performance regularly | Medium
REC-007 | Performance Monitoring | Transportation performance is difficult to monitor manually | Use Power BI dashboard for regular KPI monitoring | High
REC-008 | Data Quality | Transportation data requires validation before analysis | Perform regular data quality checks | Medium
REC-009 | Vendor Management | Vendor performance can vary by service quality | Track vendor delays, cancellations and costs using KPIs | Medium
REC-010 | Employee Experience | Waiting time and delays affect employee commute experience | Monitor waiting time and delay trends regularly | High

## Action_Plan
Action ID | Recommendation ID | Action | Responsible Team | Timeline | Priority
ACT-001 | REC-001 | Review capacity for high-demand routes | Transport Team | 1 Month | High
ACT-002 | REC-002 | Review vehicle size for low-utilization routes | Transport Team | 1 Month | High
ACT-003 | REC-003 | Review low-demand route frequency | Transport Team | 1-2 Months | Medium
ACT-004 | REC-004 | Adjust schedules for peak-hour traffic | Transport Team | 1 Month | High
ACT-005 | REC-005 | Identify backup vehicles for critical routes | Transport Team / Vendor | 1 Month | High
ACT-006 | REC-006 | Compare vendor cost and performance | Finance / Transport Team | Monthly | Medium
ACT-007 | REC-007 | Monitor transportation KPIs through Power BI | Management / Transport Team | Ongoing | High
ACT-008 | REC-008 | Perform monthly data quality checks | Admin / Transport Team | Monthly | Medium
ACT-009 | REC-009 | Review vendor performance monthly | Transport Manager | Monthly | Medium
ACT-010 | REC-010 | Monitor waiting time and delay trends | Transport Manager | Monthly | High

## Expected_Benefits
Benefit ID | Recommendation ID | Expected Benefit
BEN-001 | REC-001 | Better capacity availability on high-demand routes
BEN-002 | REC-002 | Better vehicle utilization and lower unused capacity
BEN-003 | REC-003 | Better route efficiency
BEN-004 | REC-004 | Reduced impact of traffic-related delays
BEN-005 | REC-005 | Reduced disruption caused by vehicle breakdowns
BEN-006 | REC-006 | Better transportation cost control
BEN-007 | REC-007 | Faster identification of operational problems
BEN-008 | REC-008 | More reliable analysis and reporting
BEN-009 | REC-009 | Better vendor performance management
BEN-010 | REC-010 | Improved employee commute experience